## Workplan timeline
[8 empty] | 2015 | [24 empty] | 2016 | [49 empty] | 2017
| Workplan/Technical Work Timeline | Jan '14 |  |  | Cost |  |  | July |  |  |  | Aug |  |  |  | Sept |  |  |  | Oct |  |  |  | Nov |  |  |  |  | Dec |  |  |  | Jan |  |  |  | Feb |  |  |  | Mar |  |  |  | Apr |  |  |  | May |  |  |  | Jun |  |  |  | Jul |  |  |  | Aug |  |  |  |  | Sep |  |  |  | Oct |  |  |  |  | Nov |  |  |  | Dec |  |  |  | Jan |  |  |  |  | Feb |  |  |  | Mar |  |  |  | Apr |  |  |  | May |  |  |  |  | Jun |  |  |  | Jul |  |  |  |  | Aug |  |  |  | Sep |  |  |  | Oct |  |  |  |  | Nov |  |  |  | Dec
|  | 6 | 13 | 20 | One Time | Monthly Cost | Annual Cost | 6 | 13 | 20 | 27 | 3 | 10 | 17 | 24 | 7 | 14 | 21 | 28 | 5 | 12 | 19 | 26 | 2 | 9 | 16 | 23 | 30 | 7 | 14 | 21 | 28 | 4 | 11 | 18 | 25 | 1 | 8 | 15 | 22 | 7 | 14 | 21 | 28 | 4 | 11 | 18 | 25 | 7 | 14 | 21 | 28 | 7 | 14 | 21 | 28 | 4 | 11 | 18 | 25 | 1 | 8 | 15 | 22 | 29 | 5 | 12 | 19 | 26 | 3 | 10 | 17 | 24 | 31 | 7 | 14 | 21 | 28 | 5 | 12 | 19 | 26 | 2 | 9 | 16 | 23 | 30 | 6 | 13 | 20 | 27 | 6 | 13 | 20 | 27 | 3 | 10 | 17 | 24 | 1 | 8 | 15 | 22 | 29 | 5 | 12 | 19 | 26 | 3 | 10 | 17 | 24 | 31 | 7 | 14 | 21 | 28 | 4 | 11 | 18 | 25 | 1 | 8 | 15 | 22 | 29 | 6 | 13 | 20 | 27 | 4 | 11 | 18 | 25
- | Task Force & Work Group meetings (TTWG and TF) |  |  | 22 |  |  |  | July 6: 1; July 27: 29; Aug 3: 5; Sept 7: 2; Sept 14: 3; Sept 28: 23; Oct 5: 7; Oct 26: 28; Nov 2: 4; Nov 16: 18; Dec 7: 2; Dec 14: 16; Jan 4: 6; Jan 25: 27; Feb 1: 3; Feb 22: 24; Mar 7: 2; Mar 21: 23; Apr 4: 6; Apr 25: 27; May 7: 4; May 28: 25; Jun 7: 1; Jun 28: 22; Jul 4: 6; Jul 25: 27; Aug 1: 3; Aug 29: 24; Sep 5: 7; Sep 26: 28; Oct 3: 5; Oct 31: 26; Nov 7: 2; Nov 14: 16; Dec 5: 7; Dec 12: 14?; Dec 19: 21?; Jan 2: 4; Jan 23: 25; Feb 6: 1; Feb 20: 22; Mar 6: 1; Mar 20: 22; Apr 3: 5; Apr 24: 26; May 1: 3; May 22: 24; Jun 5: 7; Jun 26: 28; Jul 3: 6; Jul 24: 26; Aug 7: 2; Aug 21: 23; Sep 4: 6; Sep 25: 27; Oct 1: 4; Oct 22: 25; Nov 6: 1; Nov 27: 29; Dec 4: 6; Dec 11: 13?; Dec 18: 20?
1 | SRRTTF Administrative Activities
| Ruckelshaus | [5 empty] | 72500
| High Volume Sampling “Proofing” |  |  |  | 65000
| Workshop |  |  |  | 10000
| Administrative Expenses | [5 empty] | 5000
2 | Annual Report/Work Plan??
3 | Technical Activities
| Incidental Sampling |  |  |  | ? | ? | ?
| Dry Weather Sampling |  |  |  | 65000
Barker to Trent
Trent to Green Street
| Groundwater - Up-Gradient of Kaiser Property |  |  |  | $70,000 to $130,000
| Retrospective Loading Analysis |  |  |  | 7500
| Groundwater - Up-Gradient of Barker-Trent |  |  |  | $55,000 to $130,000
| Hangman Creek Wet Weather |  |  |  | 27000
| Trent Gage | [5 empty] | 20000
| Nine Mile Gage |  |  |  | 25000 |  | 20000
| City of Spokane Wet Weather |  |  |  | 14000
Other Proposed Future Work
Grab vs. High Volume Sampler (Contamination from sampler/tubing) congener analysis/removal
Homolog/congener analysis (water and fish)
LimnoTech
| Develop Monitoring Scopes |  |  |  | 5000
| Meeting Participation |  |  |  |  | 1200
| Workshop Participation |  |  |  | 5000
| Update Dry Weather Mass Balances |  |  |  | 7500
| Assess Wet Weather Loads |  |  |  | 5000
| Assess Groundwater Loads |  |  |  | 7500
| Reporting |  |  |  | 5000
| Project Management |  |  |  |  | 400
4 | Comprehensive Plan
5 | EAP and SWAT Team Projects | bar: July 6; Aug 3; Sept 7; Oct 5; Nov 2; Dec 7; Jan 4; Feb 1; Feb 22; Mar 28; Apr 25; May 28; Jun 28; Jul 25; Aug 29; Sep 26; Oct 31; Nov 28; Dec 26; Jan 30; Feb 27; Mar 27; Apr 24; May 29; Jun 26; Jul 31; Aug 28; Sep 25; Oct 29; Nov 27; Dec 25
Fish Feed/fish Hatcheries
LSR Hatchery Case Study
Lake Spokane CARP
Groundwater Data Review
High Volume Sampling/Long Term Monitoring at Spokane Tribal Reservation Boundary
Atmospheric Deposition
Vactor Waste
HydroSeed
Data Management

## Techncial Activities
| Workplan/Technical Work Timeline | July |  |  |  | Aug |  |  |  | Sept |  |  |  | Oct |  |  |  | Nov |  |  |  |  | Dec |  |  |  | Jan |  |  |  | Feb |  |  |  | Mar |  |  |  | Apr |  |  |  | May |  |  |  | Jun |  |  |  | Jul |  |  |  | Aug |  |  |  |  | Sep |  |  |  | Oct |  |  |  |  | Nov |  |  |  | Dec
|  | 6 | 13 | 20 | 27 | 3 | 10 | 17 | 24 | 7 | 14 | 21 | 28 | 5 | 12 | 19 | 26 | 2 | 9 | 16 | 23 | 30 | 7 | 14 | 21 | 28 | 4 | 11 | 18 | 25 | 1 | 8 | 15 | 22 | 7 | 14 | 21 | 28 | 4 | 11 | 18 | 25 | 7 | 14 | 21 | 28 | 7 | 14 | 21 | 28 | 4 | 11 | 18 | 25 | 1 | 8 | 15 | 22 | 29 | 5 | 12 | 19 | 26 | 3 | 10 | 17 | 24 | 31 | 7 | 14 | 21 | 28 | 5 | 12 | 19 | 26
- | Task Force & Work Group meetings (TTWG and TF) | July 6: 1; July 20: 22; Aug 3: 5; Aug 24: 26; Sept 7: 2; Sept 28: 23; Oct 5: 7; Oct 26: 28; Nov 2: 4; Nov 16: 18; Dec 7: 2; Dec 14: 16; Jan 4: 6; Jan 25: 27; Feb 1: 3; Feb 22: 24; Mar 7: 2; Mar 21: 23; Apr 4: 6; Apr 25: 27; May 7: 4; May 28: 25; Jun 7: 1; Jun 28: 22; Jul 4: 6; Jul 25: 27; Aug 1: 3; Aug 29: 24; Sep 5: 7; Sep 26: 28; Oct 3: 5; Oct 31: 26; Nov 7: 2; Nov 14: 16; Dec 5: 7; Dec 12: 14?; Dec 19: 21?
3 | Technical Activities