## Sheet1
Control Actions Timeline / Tracking |  | January |  | February |  | March |  | April |  | May |  | June |  | July |  | August |  | September |  | October |  | November |  | December |  | Jan. 2018 |  | Feb. 2018 |  | Mar. 2018 |  | Apr. 2018 |  | May, 2018 |  | Jun. 2018 |  | Jul. 2018 |  | Aug. 2018 |  | Sep. 2018 |  | Oct. 2018 |  | Nov. 2018 |  | Dec. 2018
|  | 2017-01-18 | 2017-01-25 | 2017-02-01 | 2017-02-22 | 2017-03-01 | 2017-03-29 | 2017-04-05 | 2017-04-26 | 2017-05-03 | 2017-05-31 | 2017-06-07 | 2017-06-28 | 2017-07-05 | 2017-07-26 | 2017-08-02 | 2017-08-30 | 2017-09-06 | 2017-09-27 | 2017-10-04 | 2017-10-25 | 2017-11-01 | 2017-11-15 | 2017-12-06 | 2017-12-13 | 2018-01-03 | 2018-01-31 | 2018-02-07 | 2018-02-28 | 2018-03-07 | 2018-03-28 | 2018-04-04 | 2018-04-25 | 2018-05-02 | 2018-05-30 | 2018-06-06 | 2018-06-27 | 2018-07-04 | 2018-07-25 | 2018-08-01 | 2018-08-22 | 2017-09-05 | 2018-09-26 | 2018-10-03 | 2018-10-24 | 2018-11-07 | 2018-11-14 | 2018-12-05 | 2018-12-12
X in Target Date for Report to TF/TTWG (SRRTTF Meeting dates: TF, TTWG, EO, Other?) |  |  | TF | TTWG,EO | TF | TTWG,EO |  | TTWG,EO | TF | TTWG,EO |  | TTWG,EO | TF | TTWG,EO? | TF | TTWG,EO? |  | TTWG, EO? | TF | TTWG, EO? | TF | TTWG, EO? | TF | TTWG, EO? | TF | TTWG, EO? | TF | TTWG, EO? | TF | TTWG, EO? | TF | TTWG, EO? | TF | TTWG, EO? | TF | TTWG, EO? | TF | TTWG, EO? | TF | TTWG, EO? | TF | TTWG, EO? | TF | TTWG, EO? | TF | TTWG, EO? | TF | TTWG, EO? | TF
Control Action /Tasks | Task Assigned to?
(5.14.1 & 5.14.2) Data Analysis | Owners: Adriane, Bud, Mike H., et al
Conduct Barker Road to Plante's Ferry Analysis (5.14.1, 5.14.2: Conduct Mass Balance & characterize "unknown source" parameters)
Compile Available GW Data (Kaiser onsite data, up-gradient data)
Conduct Appropriate Data Analysis
Pursue Identification of Potential Source(s): 10 Most Prevalent Congeners, Ecology TCP Files Review (?), Groundwater Investigations (?)
Conduct Plante's Ferry to Green Street Analysis (5.14.1, 5.14.2)
Conduct Appropriate Data Analysis (Rodenburg?)
Pursue Identification of Potential Source(s): 10 Most Prevalent Congeners, Ecology TCP Files Review (?), Groundwater Investigations (?)
Conduct Green Street to Spokane Gage Analysis (5.14.1, 5.14.2)
Conduct Appropriate Data Analysis (Rodenburg?)
Pursue Identification of Potential Source(s): 10 Most Prevalent Congeners, Ecology TCP Files Review (?), Groundwater Investigations (?)
Compile 2012 Ecology Fish Data on Spokane River (6.3.1: Compile Available Sediment Data on Spokane River Relative to Fish Data)
Total PCB Concentrations
Blank-corrected Congener Levels
Blank-corrected Homologue Levels
10 Most Prevalent Concentration Congeners
Compare Fish Tissue & Sediment Data
Conduct comparative analysis between fish data locations & sediment data locations
Adequate overlap of fish & sediment data? Additional sediment data collection? Collection of Biota Data?
(5.8.2) Green Chemistry Alternatives | Owners: Adriane, Bud, Mike H., et al
Plan for providing guidance & feedback to Ecology on Green Chemistry efforts
Plan to assist Ecology's efforts to contact outside parties, i.e. - EPA & universities
(5.13.1) Demolition & Renovation Control | Owners: County (Toni Taylor), Ecology, City of Spokane, Mike L./SRHD, Post Falls
Plan to adapt SFEP information to a Spokane focused document
Plan to integrate document into existing building demolition & renovation permits
(5.9.2) Waste Disposal Assistance | Owners: Mike L./SRHD
Plan for making recommendations to organizations on better control of PCB waste
(E&O): Plan for public education relative to identification & disposal of PCB waste
(5.10.2) Regulatory Rulemaking | Owners: Doug (TSCA), Greg L./WSDOT (road paint color box)
Plan for addressing color box requirements road paints | Greg Lahti
Control Actions not Requiring Work Plan but with Milestones in 9/14/16 Comp Plan Draft
(5.11.2) Regulatory Compliance | Owners: TBD
TTWG Review of EAP Spokane atmospheric deposition study during public review period
Conduct assessment of results relative to need for additional regulatory controls
(5.12.2) Emerging Stormwater Technologies | Owners: TBD
TTWG review Phase 1 study results
Conduct assessment of appropriate support for future studies
(5.8.2) PCB Product Testing | Owners: TBD
TF to Provide guidance & feedback to Ecology on product testing report
Product Testing Strategy
Assist Ecology with centralized clearinghouse for testing information
E&O: Conduct public education on product testing results