## Work Plan Steps
Control Actions Timeline / Tracking |  | January |  | February |  | March |  | April |  | May |  | June |  | July |  | August |  | September |  | October |  | November |  | December
|  | 2017-01-18 | 2017-01-25 | 2017-02-01 | 2017-02-22 | 2017-03-01 | 2017-03-29 | 2017-04-05 | 2017-04-26 | 2017-05-03 | 2017-05-31 | 2017-06-07 | 2017-06-28 | 2017-07-05 | 2017-07-26 | 2017-08-02 | 2017-08-30 | 2017-09-06 | 2017-09-27 | 2017-10-04 | 2017-10-25 | 2017-11-01 | 2017-11-15 | 2017-12-06 | 2017-12-13
X in Target Date for Report to TF/TTWG (SRRTTF Meeting dates: TF, TTWG, EO, Other?) |  |  | TF | TTWG, EO | TF | TTWG, EO |  | TTWG, EO | TF | TTWG, EO |  | TTWG, EO | TF | TTWG, EO? | TF | TTWG, EO? |  | TTWG, EO? | TF | TTWG, EO? | TF | TTWG, EO? | TF | TTWG, EO? | TF
Control Action /Tasks | Task Assigned to?
(5.14.1 & 5.14.2) Data Analysis to ID Sites of Concern for Contaminated GW | Owners: Adriane, Bud, Mike H., et al
Conduct Barker Road to Plante's Ferry Analysis (5.14.1, 5.14.2: Conduct Mass Balance & characterize "unknown source" parameters) |  | 2017-12-13: impl. review
Compile available GW Data (Kaiser onsite data, up-gradient data) |  | 2017-12-13: impl. review
Conduct Appropriate Data Analysis |  | 2017-12-13: impl. review
Pursue Identification of Potential Source(s): 10 Most Prevalent Congeners, Ecology TCP Files Review (?), Groundwater Investigations (?) |  | 2017-12-13: impl. review
Conduct Plante's Ferry to Green St. Analysis (5.14.1, 5.14.2) |  | 2017-12-13: impl. review
Conduct Appropriate Data Analysis (Rodenburg?) |  | 2017-12-13: impl. review
Pursue Identification of Potential Source(s): 10 Most Prevalent Congeners, Ecology TCP Files Review (?), Groundwater Investigations (?) |  | 2017-12-13: impl. review
Conduct Green Street to Spokane Gage Analysis (5.14.1, 5.14.2) |  | 2017-12-13: impl. review
Conduct Appropriate Data Analysis (Rodenburg?) |  | 2017-12-13: impl. review
Pursue Identification of Potential Source(s): 10 Most Prevalent Congeners, Ecology TCP Files Review (?), Groundwater Investigations (?) |  | 2017-12-13: impl. review
(5.8.2) Green Chemistry Alternatives | Owners: Adriane, Bud, Mike H., et al
Plan for providing guidance & feedback to Ecology on Green Chemistry efforts |  | 2017-12-13: impl. review
Plan to assist Ecology's efforts to contact outside parties, i.e. - EPA & universities |  | 2017-12-13: impl. review
(5.13.1) Demolition & Renovation Control | Owners: County (Toni Taylor), Ecology, City of Spokane, Mike L./SRHD, Post Falls
Ecology survey of WSDOT buildings to assess prevalence of PCBs (to inform SFEP materials) |  | 2017-12-13: impl. review
Adapt SFEP information to a Spokane-focused document |  | 2017-12-13: impl. review
Plan to integrate document into existing building demolition & renovation permits |  | 2017-12-13: impl. review
(5.9.2) Waste Disposal Assistance | Owners: Mike L./SRHD
Plan for making recommendations to organizations on better control of PCB waste |  | 2017-12-13: impl. review
(E&O): Plan for public education relative to identification & disposal of PCB waste |  | 2017-12-13: impl. review
(5.10.2) Regulatory Rulemaking | Owners: Doug (TSCA), Greg L./WSDOT (road paint color box)
Plan for addressing color box requirements road paints | Greg Lahti | 2017-12-13: impl. review
Control Actions not Requiring Work Plan but with Milestones in 9/14/16 Comp Plan Draft
(5.11.2) Regulatory Compliance | Owners: TBD
TTWG Review of EAP Spokane atmospheric deposition study during public review period |  | 2017-12-13: impl. review
Conduct assessment of results relative to need for additional regulatory controls |  | 2017-12-13: impl. review
(5.12.2) Emerging Stormwater Technologies | Owners: NPDES Permittees
TTWG review Phase 1 study results |  | 2017-12-13: impl. review
Conduct assessment of appropriate support for future studies |  | 2017-12-13: impl. review
5.15.2 Education and Outreach (not a specific action- but called out to develop a work plan (page 68, many action items delineate education and outreach)
Work Group Meets monthly (First Wednesday of month) | bar: 2017-02-01; 2017-03-01; 2017-04-05; 2017-05-03; 2017-06-07; 2017-07-05; 2017-08-02; 2017-09-06; 2017-10-04; 2017-11-01; 2017-12-06
Task 1: Inventory of edcuation and outreach work and outreach system map | Brenden Campbell and Kara Whitman
Task 2. Develop webspace for all education and outreach materials | Owners: Kristen Zimmer/Kara Whitman | bar: 2017-03-01 to 2017-04-26
Task 2.1 Mock up of web space | Kristen Zimmer | bar: 2017-02-01 to 2017-02-22
(5.8.2) PCB Product Testing | Owners: TBD
TF to Provide guidance & feedback to Ecology on product testing report |  | 2017-12-13: impl. review
Product Testing Strategy |  | 2017-12-13: impl. review
Assist Ecology with centralized clearinghouse for testing information |  | 2017-12-13: impl. review
E&O: Conduct public education on product testing results |  | 2017-12-13: impl. review

## Future Studies
Comp Plan Implementation Timeline / Tracking |  | January |  | February |  | March |  | April |  | May |  | June |  | July |  | August |  | September |  | October |  | November |  | December
| Task Assigned to? | 2017-01-18 | 2017-01-25 | 2017-02-01 | 2017-02-22 | 2017-03-01 | 2017-03-29 | 2017-04-05 | 2017-04-26 | 2017-05-03 | 2017-05-31 | 2017-06-07 | 2017-06-28 | 2017-07-05 | 2017-07-26 | 2017-08-02 | 2017-08-30 | 2017-09-06 | 2017-09-27 | 2017-10-04 | 2017-10-25 | 2017-11-01 | 2017-11-15 | 2017-12-06 | 2017-12-13
X in Target Date for Report to TF/TTWG (SRRTTF Mtg dates: TF, TTWG, EO, Other?) |  |  | TF | TTWG, EO | TF | TTWG, EO |  | TTWG, EO | TF | TTWG, EO |  | TTWG, EO | TF | TTWG, EO? | TF | TTWG, EO? |  | TTWG, EO? | TF | TTWG, EO? | TF | TTWG, EO? | TF | TTWG, EO? | TF
(6.1) Implementation Effectiveness Assessment
(6.2) Consideration of Additional Control Actions
(6.2.1) Education on Septic Disposal
(6.2.2) Survey Schools and Public Buildings
(6.2.3) Accelerated Sewer Construction
6.2.4 Emerging Wastewater Technology
6.2.5 Survey of Local Electrical Equipment
6.2.6 Leak Prevention/ Detection in Electrical Equipment
6.2.7 Regulation of Waste Disposal
6.2.8 Stormwater Source Tracing
6.2.9 Removal of Carp from Lake Spokane
6.2.10 PCB Identification during Inspections
6.2.11 Compliance with PCB Regulations
(6.3.1) Compile 2012 Ecology Fish Data on Spokane River (6.3.1: Compile Available Sediment Data on Spokane River Relative to Fish Data)
Total PCB Concentrations
Blank-corrected Congener Levels
Blank-corrected Homologue Levels
10 Most Prevalent Concentration Congeners
Compare Fish Tissue & Sediment Data
Conduct comparative analysis between fish data locations & sediment data locations
Adequate overlap of fish & sediment data? Additional sediment data collection? Collection of Biota Data?