## Category A
| Comp Plan Implementation Timeline / Tracking |  | January |  | February |  | March |  | April |  | May |  | June |  | July |  | August |  | September |  | October |  | November |  | December
Comp Plan Reference |  |  | 2017-01-18 | 2017-01-25 | 2017-02-01 | 2017-02-22 | 2017-03-01 | 2017-03-29 | 2017-04-05 | 2017-04-26 | 2017-05-03 | 2017-05-31 | 2017-06-07 | 2017-06-28 | 2017-07-05 | 2017-07-26 | 2017-08-02 | 2017-08-30 | 2017-09-06 | 2017-09-27 | 2017-10-04 | 2017-10-25 | 2017-11-01 | 2017-11-15 | 2017-12-06 | 2017-12-13
| X in Target Date for Report to TF/TTWG (SRRTTF Meeting dates: TF, TTWG, EO, Other?) |  |  | TF | TTWG,EO | TF | TTWG,EO |  | TTWG,EO | TF | TTWG,EO |  | TTWG,EO | TF | TTWG,EO? | TF | TTWG,EO? |  | TTWG, EO? | TF | TTWG, EO? | TF | TTWG, EO? | TF | TTWG, EO? | TF
| Implementation Tasks | Task Assigned to?
p 49 | 5.1 Wastewater Treatment
Meet permit requirements
5.1.1 Idaho Municipal Permits | Participate in the SRRTTF | City of Coeur d'Alene City of Post Falls Hayden Area Regional Sewer Board | bar: 2017-01-25; 2017-02-22; 2017-04-26; 2017-06-28; 2017-07-26; 2017-09-27; 2017-10-25; 2017-11-15; 2017-12-13
5.1.2 Washington Municipal Permits |  | City of Liberty Lake City of Spokane Spokane County
5.1.3 Washington Industrial Permits |  | Kaiser Aluminum Inland Empire Paper
5.1.4 Fish Hatchery Permits |  | Spokane Fish Hatchery Ford Fish Hatchery Spokane Tribal Hatchery
p. 53 | 5.2 Remediate Known Contaminated Sites
5.2.1 Spokane River Upriver Dam and Donkey Island | Continue monitoring the effectiveness of the remedial action and the integrity of the cap at a rate of once every five years to ensure long-term protectiveness | Ecology
5.2.2 General Electric Co. | Continue monitoring the effectiveness of the remedial action and the integrity of the cap at a rate of once every five years to ensure long-term protectiveness | Ecology
5.2.3 City Parcel | Continue monitoring the effectiveness of the remedial action and the integrity of the cap at a rate of once every five years to ensure long-term protectiveness | Ecology
5.2.4 Kaiser Aluminum | Complete groundwater pilot treatment study and issue clean-up action plan | Ecology/Kaiser
p. 55 | 5.3 Stormwater Controls | Owners: TBD
5.3.1 NPDES Stormwater Permits for MS4s | Meet permit requirements | City of Spokane City of Spokane Valley Spokane County Washington State DOT City of Post Falls City of Coeur d'Alene Post Falls Highway District Lakes Highway District Idaho Transportation Department
5.3.2 City of Spokane's Integrated Clean Water Plan | Implement planned actions | City of Spokane
| Meet CSO Performance Standard | City of Spokane
p. 57 | 5.4 Low Impact Development Ordinance
5.4 Low Impact Development Ordinance | Encourage use of LID with financial incentive for developers | City of Spokane
p. 57 | 5.5 Street Sweeping
5.5 Street Sweeping | Continue existing practices and schedules | City of Spokane City of Spokane Valley Spokane County City of Post Falls City of Coeur d'Alene
p. 58 | 5.6 Purchasing Standards
5.6 Purchasing Standards | Continue existing practices for preferential purchasing of PCB-free products when cost-effective and technically feasible | State of Washington City of Spokane Spokane County

## Category B
| Comp Plan Implementation Timeline / Tracking |  | January |  | February |  | March |  | April |  | May |  | June |  | July |  | August |  | September |  | October |  | November |  | December
Comp Plan Reference |  |  | 2017-01-18 | 2017-01-25 | 2017-02-01 | 2017-02-22 | 2017-03-01 | 2017-03-29 | 2017-04-05 | 2017-04-26 | 2017-05-03 | 2017-05-31 | 2017-06-07 | 2017-06-28 | 2017-07-05 | 2017-07-26 | 2017-08-02 | 2017-08-30 | 2017-09-06 | 2017-09-27 | 2017-10-04 | 2017-10-25 | 2017-11-01 | 2017-11-15 | 2017-12-06 | 2017-12-13
| X in Target Date for Report to TF/TTWG (SRRTTF Meeting dates: TF, TTWG, EO, Other?) |  |  | TF | TTWG,EO | TF | TTWG,EO |  | TTWG,EO | TF | TTWG,EO |  | TTWG,EO | TF | TTWG,EO? | TF | TTWG,EO? |  | TTWG, EO? | TF | TTWG, EO? | TF | TTWG, EO? | TF | TTWG, EO? | TF
| Tasks (Orange = Work Plan; Blue = no work plan, milestones in 9/14/16 Comp Plan draft | Task Assigned to?
p. 58 | 5.7 Support of Green Chemistry Alternatives | See Green Chemistry Work Plan
5.7.1 Existing Actions | Provide technical support to educators; Incorporate green chemistry into teaching materials; Provide info to public about safer choices; Partner w/orgs e.g. NW Green Chemistry, Green Chemistry Institute; Support research activities & the Presidential Green Chemistry Challenge | Ecology (Green Chemistry Work Group)
5.7.2 New Actions | Provide guidance & feedback to Ecology on current and potential ongoing Green Chemistry efforts; Plan to assist Ecology's efforts to contact outside parties, i.e. - EPA & universities | Adriane Borgias; Doug Greenlund; Saskia Van Bergen; Mike Petersen; Kara Whitman | bar: 2017-02-22; 2017-04-26; 2017-07-26; 2017-10-25
Milestone Activities p 67 | Demonstrated tangible outreach to Ecology, EPA, and/or universities | bar: 2017-02-22; 2017-04-26; 2017-07-26; 2017-10-25
Tangible improvement in Green Chemistry efforts due to Task Force actions | bar: 2017-02-22; 2017-04-26; 2017-07-26; 2017-10-25
p.59 | 5.8 PCB Product Testing
5.8.1 Existing Actions | Testing and reporting of PCBs in consumer products | Ecology City of Spokane
| Centralized database for consumer products testing | Ecology
5.8.2 New Actions |  | Green Chemistry Work Group
Milestone Activity | Provide guidance & feedback to Ecology on product testing report within public comment period for draft report | Full Task Force
| Support development of a centralized clearing house containing PCB product testing information | Green Chemistry Work Group
Milestone Activities | Initial outreach to Ecology to determine if/how Task Force can provide support
Definition of the specific support to be provided
| Provision of support Provide input to Ecology in support of its efforts toward development of a clearinghouse by November 2017 | Full Task Force or individual members as appropriate | 2017-11-01: Work-sheet Qs
| Assist Ecology with centralized clearinghouse for testing information | Green Chemistry Work Group
| Conduct public education on products containing PCBs | Green Chemistry Work Group Education and Outreach Work Group | bar: 2017-02-22; 2017-04-26; 2017-07-26; 2017-10-25
Milestone Activity | Annual Review of outreach activity | bar: 2017-02-22; 2017-04-26; 2017-07-26; 2017-10-25 to 2017-11-01
p.59 | 5.9 Waste Disposal Assistance | Owners: Mike L./SRHD
5.9.1 Existing Actions | Spokane River Forum Waste Directory Spokane Envirostars | Spokane River Forum
| Mercury-Containing Lights Product Stewardship | Ecology
| Electronic Waste recycling | Ecology Idaho DEQ
5.9.2 New Actions | Provide recommendations to implementing organizations on better control of PCB waste | Urban Waters Education and Outreach
See Waste Disposal Work Plan sheet | Plan for public education relative to identification & disposal of PCB waste | Urban Waters Education and Outreach
Milestone Activities p 67 | Specific recommendations provided to implementing organizations
Evidence of raised public awareness on how to identify and dispose of PCB
p. 60 | 5.10 Regulatory Rulemaking | Owners: Doug (TSCA), Greg L./WSDOT (road paint color box)
5.10.1 Existing Actions | Continuing Engagement with State and Federal agencies regarding reform of existing regulations | TSCA Work Group
See Regulatory Rulemaking Work Plan sheet | Provide evaluation and comment on rulemaking activities | TSCA Work Group
Milestone activitiesp 68 | Existing and ongoing dialog with
EPA regarding TSCA reform
FDA regarding food packaging
5.10.2 New Actions | Seek state/federal changes to color box requirements road paints, allowing for use of PCB-free paints | WSDOT Department of Enterprise Services | bar: 2017-02-22; 2017-04-26; 2017-07-26; 2017-10-25
Milestone Activities p 68 | Outreach regarding road paint and color box requirements | bar: 2017-02-22; 2017-04-26; 2017-07-26; 2017-10-25
Governmental agencies
Paint manufacturers
p. 60 | 5.11 Regulatory Compliance
5.11.1 Existing Actions | Engagement with State and federal agencies, providing comments on permits and regulatory activities (Milestone activity: maintain existing activity)
5.11.2 New Actions
Milestone Activities | Review of EAP Spokane atmospheric deposition study during public review period | TTWG
| Assess need for regulatory control of atmospheric PCB sources such as used oil burning. | TTWG
| Support agencies on regulatory revisions regarding the relevant sources. | TTWG
p. 61 | 5.12 Emerging End of Pipe Stormwater Technologies
5.12.1 Existing Actions | Complete Phase 1 of Fungi study | The Lands Council
5.12.1 New Actions
Milestone Activities | Review Phase 1 study results within 1 year of report | TTWG
Submit comments
| Conduct assessment of appropriate support for future studies within 3 months of submittal of comments | TTWG | bar: 2017-02-22; 2017-04-26; 2017-07-26; 2017-10-25

## Category C
| Comp Plan Implementation Timeline / Tracking |  | January |  | February |  | March |  | April |  | May |  | June |  | July |  | August |  | September |  | October |  | November |  | December
Comp Plan Reference |  |  | 2017-01-18 | 2017-01-25 | 2017-02-01 | 2017-02-22 | 2017-03-01 | 2017-03-29 | 2017-04-05 | 2017-04-26 | 2017-05-03 | 2017-05-31 | 2017-06-07 | 2017-06-28 | 2017-07-05 | 2017-07-26 | 2017-08-02 | 2017-08-30 | 2017-09-06 | 2017-09-27 | 2017-10-04 | 2017-10-25 | 2017-11-01 | 2017-11-15 | 2017-12-06 | 2017-12-13
| X in Target Date for Report to TF/TTWG (SRRTTF Meeting dates: TF, TTWG, EO, Other?) |  |  | TF | TTWG,EO | TF | TTWG,EO |  | TTWG,EO | TF | TTWG,EO |  | TTWG,EO | TF | TTWG,EO? | TF | TTWG,EO? |  | TTWG, EO? | TF | TTWG, EO? | TF | TTWG, EO? | TF | TTWG, EO? | TF
| Tasks (Orange = Work Plan; Blue = no work plan, milestones in 9/14/16 Comp Plan draft | Task Assigned to?
p. 61 | 5.13 Building Demolition & Renovation Control | Owners: County (Toni Taylor), Ecology, City of Spokane, Mike L./SRHD, Post Falls
5.13.1 Actions | Adapt SFEP information to a Spokane focused document | Building Demolition and Renovation Control Work Group
See Building Demo Work Plan | Plan to integrate document into existing building demolition & renovation permits | Education and Outreach Group
Milestone Activities p 68 | Adaptation of SFEI BMPs
Coordination with local governments for distribution with relevant permits
Demonstrated change in contractor behavior
p. 62 | 5.14 Identification of Sites of Concern for Contaminated Groundwater | TTWG
5.14.1a | Mine existing data
5.14.1b | Package Information for and Consult with TCP
5.14.1c | Determine next action
See Identify Sites of Concern Work Plan
Milestone Activities p 68 | Assessment document describing data mining activities
Coordination with Ecology's Toxics Clean up Program
Develop consensus plan for future action
Determination for each site under consideration
Is a significant contributor of PCBs to the Spokane River
Are remediation activities merited?
Initiation of remediation activities on sites determined to be significant

## Category D
| Comp Plan Implementation Timeline / Tracking |  | January |  | February |  | March |  | April |  | May |  | June |  | July |  | August |  | September |  | October |  | November |  | December
Comp Plan Reference |  |  | 2017-01-18 | 2017-01-25 | 2017-02-01 | 2017-02-22 | 2017-03-01 | 2017-03-29 | 2017-04-05 | 2017-04-26 | 2017-05-03 | 2017-05-31 | 2017-06-07 | 2017-06-28 | 2017-07-05 | 2017-07-26 | 2017-08-02 | 2017-08-30 | 2017-09-06 | 2017-09-27 | 2017-10-04 | 2017-10-25 | 2017-11-01 | 2017-11-15 | 2017-12-06 | 2017-12-13
| X in Target Date for Report to TF/TTWG (SRRTTF Meeting dates: TF, TTWG, EO, Other?) |  |  | TF | TTWG,EO | TF | TTWG,EO |  | TTWG,EO | TF | TTWG,EO |  | TTWG,EO | TF | TTWG,EO? | TF | TTWG,EO? |  | TTWG, EO? | TF | TTWG, EO? | TF | TTWG, EO? | TF | TTWG, EO? | TF
| Tasks (Orange = Work Plan; Blue = no work plan, milestones in 9/14/16 Comp Plan draft | Task Assigned to?
p.69 | 6.1 Implementation Effectiveness Assessment
| Annual Implementation Effectiveness Assessment (Due in April of each year) | Task Force
| 5-yr Implementation Effectiveness Assessment (Due April 2022) | Task Force
PCB loading to the Spokane River from the primary delivery mechanisms
| Effluent monitoring data | NPDES permittees
| Groundwater loading near Kaiser | Kaiser Remediation project
| Stormwater/CSO loading | City of Spokane
| Lake Coeur d'Alene/head of Spokane River | NPDES permittees, Idaho
| Spokane River PCB concentrations and changes in concentrations | Task Force; Ecology
pg 70 | 6.2 Consideration of Additional Control Actions
6.2.1 Education on Septic Disposal
6.2.2 Survey Schools and Public Buildings
6.2.3 Accelerated Sewer Construction
pg 71 | 6.2.4 Emerging Wastewater Technology
6.2.5 Survey of Local Electrical Equipment
6.2.6 Leak Prevention/ Detection in Electrical Equipment
6.2.7 Regulation of Waste Disposal
6.2.8 Stormwater Source Tracing
6.2.9 Removal of Carp from Lake Spokane
6.2.10 PCB Identification during Inspections
6.2.11 Compliance with PCB Regulations
pg. 72 | 6.3 Studies to Address Data Gaps
6.3.1 Key Data Gaps | Bioaccumulation of PCBs in fish
Assessment of sediment PCB concentrations
Assessment of congener patterns
PCB sources
Bottom sediments
Fish
6.3.2 Study Plan | What is the importance of water column vs. sediment sources in contributing to fish tissue contamination?
What are the likely sources of PCBs to sediments and fish?
What are the target areas for more rigourous assessment?
See Data Gaps Work Plan | Develop workplan to: Mine existing data; Compile & format data into database; Perform rigorous assessment

## 5.7 Green Chemistry Work Plan
| Comp Plan Implementation Timeline / Tracking |  | January |  | February |  | March |  | April |  | May |  | June |  | July |  | August |  | September |  | October |  | November |  | December |  | Jan. 2018 |  | Feb. 2018 |  | Mar. 2018 |  | Apr. 2018 |  | May, 2018 |  | Jun. 2018 |  | Jul. 2018 |  | Aug. 2018 |  | Sep. 2018 |  | Oct. 2018 |  | Nov. 2018 |  | Dec. 2018
Comp Plan Reference |  |  | 2017-01-18 | 2017-01-25 | 2017-02-01 | 2017-02-22 | 2017-03-01 | 2017-03-29 | 2017-04-05 | 2017-04-26 | 2017-05-03 | 2017-05-31 | 2017-06-07 | 2017-06-28 | 2017-07-05 | 2017-07-26 | 2017-08-02 | 2017-08-30 | 2017-09-06 | 2017-09-27 | 2017-10-04 | 2017-10-25 | 2017-11-01 | 2017-11-15 | 2017-12-06 | 2017-12-13 | 2018-01-03 | 2018-01-31 | 2018-02-07 | 2018-02-28 | 2018-03-07 | 2018-03-28 | 2018-04-04 | 2018-04-25 | 2018-05-02 | 2018-05-30 | 2018-06-06 | 2018-06-27 | 2018-07-04 | 2018-07-25 | 2018-08-01 | 2018-08-22 | 2017-09-05 | 2018-09-26 | 2018-10-03 | 2018-10-24 | 2018-11-07 | 2018-11-14 | 2018-12-05 | 2018-12-12
| X in Target Date for Report to TF/TTWG (SRRTTF Meeting dates: TF, TTWG, EO, Other?) |  |  | TF | TTWG,EO | TF | TTWG,EO |  | TTWG,EO | TF | TTWG,EO |  | TTWG,EO | TF | TTWG,EO? | TF | TTWG,EO? |  | TTWG, EO? | TF | TTWG, EO? | TF | TTWG, EO? | TF | TTWG, EO? | TF | TTWG, EO? | TF | TTWG, EO? | TF | TTWG, EO? | TF | TTWG, EO? | TF | TTWG, EO? | TF | TTWG, EO? | TF | TTWG, EO? | TF | TTWG, EO? | TF | TTWG, EO? | TF | TTWG, EO? | TF | TTWG, EO? | TF | TTWG, EO? | TF
| Tasks (Orange = Work Plan; Blue = no work plan, milestones in 9/14/16 Comp Plan draft | Task Assigned to?
Milestone Activitiesp 67 | Demonstrated tangible outreach to Ecology, EPA, and/or universities
Link to Comprehensive Plan item 5.7 | Tangible improvement in Green Chemistry efforts due to Task Force actions
| (5.7.2) Green Chemistry Alternatives | Owners: Adriane, Bud, Mike H., et al
| Meet quarterly and report back to Task Force |  |  |  | 2017-02-06
Communicate regularly with Ecology and remain updated on current Green Chemistry Efforts
Coordinate with the Education and Outreach Work Group outreach efforts for:
See also PCB Product Testing | General public - consumer products
See also Waste Disposal Assistance | Businesses
See also Purchasing Standards | High schools
See also Education and Outreach Work Plan | Colleges
Use available data to identify Green Chemistry opportunities
Environmental
Literature
Screening methods
Describe the nature of the problem, significance to the river and the research opportunity
Pigments
Hydroseed
Deicers
Education
Research
Report to Task Force
Support Relevant Green Chemistry Opportunities
EPA
Colleges and Universities
Innovaton challenges
Report to Task Force

## 5.9 Waste Disposal Work Plan
| Comp Plan Implementation Timeline / Tracking |  | January |  | February |  | March |  | April |  | May |  | June |  | July |  | August |  | September |  | October |  | November |  | December
Comp Plan Reference |  |  | 2017-01-18 | 2017-01-25 | 2017-02-01 | 2017-02-22 | 2017-03-01 | 2017-03-29 | 2017-04-05 | 2017-04-26 | 2017-05-03 | 2017-05-31 | 2017-06-07 | 2017-06-28 | 2017-07-05 | 2017-07-26 | 2017-08-02 | 2017-08-30 | 2017-09-06 | 2017-09-27 | 2017-10-04 | 2017-10-25 | 2017-11-01 | 2017-11-15 | 2017-12-06 | 2017-12-13
| X in Target Date for Report to TF/TTWG (SRRTTF Meeting dates: TF, TTWG, EO, Other?) |  |  | TF | TTWG,EO | TF | TTWG,EO |  | TTWG,EO | TF | TTWG,EO |  | TTWG,EO | TF | TTWG,EO? | TF | TTWG,EO? |  | TTWG, EO? | TF | TTWG, EO? | TF | TTWG, EO? | TF | TTWG, EO? | TF
| Tasks (Orange = Work Plan; Blue = no work plan, milestones in 9/14/16 Comp Plan draft | Task Assigned to?
Milestone Activitesp 67 | Specific recommendations provided to implementing organizations
Evidence of raised public awareness on how to identify and dispose of PCB
| (5.9.2) Waste Disposal Assistance | Owners: Mike L./SRHD
Link to Comprehensive Plan Waste Disposal Assistance Control Action | Provide recommendations to implementing organizations on better control of PCB waste | Urban Waters Education and Outreach
| Plan for public education relative to identification & disposal of PCB waste | Urban Waters Education and Outreach

## 5.10 Reg Rulemaking Work Plan
| Comp Plan Implementation Timeline / Tracking |  | January |  | February |  | March |  | April |  | May |  | June |  | July |  | August |  | September |  | October |  | November |  | December
Comp Plan Reference |  |  | 2017-01-18 | 2017-01-25 | 2017-02-01 | 2017-02-22 | 2017-03-01 | 2017-03-29 | 2017-04-05 | 2017-04-26 | 2017-05-03 | 2017-05-31 | 2017-06-07 | 2017-06-28 | 2017-07-05 | 2017-07-26 | 2017-08-02 | 2017-08-30 | 2017-09-06 | 2017-09-27 | 2017-10-04 | 2017-10-25 | 2017-11-01 | 2017-11-15 | 2017-12-06 | 2017-12-13
| X in Target Date for Report to TF/TTWG (SRRTTF Meeting dates: TF, TTWG, EO, Other?) |  |  | TF | TTWG,EO | TF | TTWG,EO |  | TTWG,EO | TF | TTWG,EO |  | TTWG,EO | TF | TTWG,EO? | TF | TTWG,EO? |  | TTWG, EO? | TF | TTWG, EO? | TF | TTWG, EO? | TF | TTWG, EO? | TF
| Tasks (Orange = Work Plan; Blue = no work plan, milestones in 9/14/16 Comp Plan draft | Task Assigned to?
Milestone activities p 68 | Existing and ongoing dialog with
EPA regarding TSCA reform
FDA regarding food packaging
Milestone activitiesp 68 | Outreach regarding road paint and color box requirements | bar: 2017-02-22; 2017-04-26; 2017-07-26; 2017-10-25
Governmental agencies
Paint manufacturers
| (5.10.2) Regulatory Rulemaking | Owners: Doug (TSCA), Greg L./WSDOT (road paint color box)
5.10.1 Existing Actions | Continuing Engagement with State and Federal agencies regarding reform of existing regulations | TSCA Work Group
| Provide evaluation and comment on rulemaking activities | TSCA Work Group
Link to Comprehensive Plan for Regulatory Rulemaking | Plan for addressing color box requirements road paints | Greg Lahti

## 5.13 Building Demo Work Plan
| Comp Plan Implementation Timeline / Tracking |  | January |  | February |  | March |  | April |  | May |  | June |  | July |  | August |  | September |  | October |  | November |  | December
Comp Plan Reference |  |  | 2017-01-18 | 2017-01-25 | 2017-02-01 | 2017-02-22 | 2017-03-01 | 2017-03-29 | 2017-04-05 | 2017-04-26 | 2017-05-03 | 2017-05-31 | 2017-06-07 | 2017-06-28 | 2017-07-05 | 2017-07-26 | 2017-08-02 | 2017-08-30 | 2017-09-06 | 2017-09-27 | 2017-10-04 | 2017-10-25 | 2017-11-01 | 2017-11-15 | 2017-12-06 | 2017-12-13
| X in Target Date for Report to TF/TTWG (SRRTTF Meeting dates: TF, TTWG, EO, Other?) |  |  | TF | TTWG,EO | TF | TTWG,EO |  | TTWG,EO | TF | TTWG,EO |  | TTWG,EO | TF | TTWG,EO? | TF | TTWG,EO? |  | TTWG, EO? | TF | TTWG, EO? | TF | TTWG, EO? | TF | TTWG, EO? | TF
| Tasks (Orange = Work Plan; Blue = no work plan, milestones in 9/14/16 Comp Plan draft | Task Assigned to?
Milestone Activities p 68 | Adaptation of SFEI BMPs
Coordination with local governments for distribution with relevant permits
Demonstrated change in contractor behavior
| (5.13.1) Demolition & Renovation Control | Owners: County (Toni Taylor), Ecology, City of Spokane, Mike L./SRHD, Post Falls
Link to Comprehensive Plan Building Demolition and Rennovation Control | Adapt SFEP information to a Spokane focused document
Gain better understanding of situation in Spokane
Link to SFEI's BMP document | Complete Urban Waters project on properties in Spokane | Urban Waters | bar: 2017-01-18 to 2017-09-27
Use results of study to inform adaptation of SFEI information | bar: 2017-01-18 to 2017-09-27
Use process flow chart (below) to determine next steps
| Plan to integrate document into existing building demolition & renovation permits | Education and Outreach

## 5.14 ID Sites Work Plan
| Comp Plan Implementation Timeline / Tracking |  | January |  | February |  | March |  | April |  | May |  | June |  | July |  | August |  | September |  | October |  | November |  | December
Comp Plan Reference |  |  | 2017-01-18 | 2017-01-25 | 2017-02-01 | 2017-02-22 | 2017-03-01 | 2017-03-29 | 2017-04-05 | 2017-04-26 | 2017-05-03 | 2017-05-31 | 2017-06-07 | 2017-06-28 | 2017-07-05 | 2017-07-26 | 2017-08-02 | 2017-08-30 | 2017-09-06 | 2017-09-27 | 2017-10-04 | 2017-10-25 | 2017-11-01 | 2017-11-15 | 2017-12-06 | 2017-12-13
| X in Target Date for Report to TF/TTWG (SRRTTF Meeting dates: TF, TTWG, EO, Other?) |  |  | TF | TTWG,EO | TF | TTWG,EO |  | TTWG,EO | TF | TTWG,EO |  | TTWG,EO | TF | TTWG,EO? | TF | TTWG,EO? |  | TTWG, EO? | TF | TTWG, EO? | TF | TTWG, EO? | TF | TTWG, EO? | TF
| Tasks (Orange = Work Plan; Blue = no work plan, milestones in 9/14/16 Comp Plan draft | Task Assigned to?
Milestone Activities p 68 | Assessment document describing data mining activities
Coordination with Ecology's Toxics Clean up Program
Develop consensus plan for future action
Determination for each site under consideration
Is a significant contributor of PCBs to the Spokane River
Are remediation activities merited?
Initiation of remediation activities on sites determined to be significant
| (5.14.1 & 5.14.2) Identification of Sites of Concern for Contaminated Groundwater | Owners: Adriane, Bud, Mike H., et al
Link to Comprehensive Plan ID of sites Control Action | Compile Available Data
Ambient Stations
Point Source
Groundwater
Pursue Identification of Potential Source(s): 10 Most Prevalent Congeners, Ecology TCP Files Review (?), Groundwater Investigations (?)
Conduct Surface Water Data Analysis
Barker Road to Plante's Ferry
Plante's Ferry to Greene Street
Greene Street to Spokane Gauge
Spokane Gauge to Ninemile
Conduct Groundwater Data Analysis
[Add Link to Bud Leber Flow chart] | Conduct Site Records Search
Document Groundwater Data Analysis

## 6.3 Data Gaps Work Plan
| Comp Plan Implementation Timeline / Tracking |  | January |  | February |  | March |  | April |  | May |  | June |  | July |  | August |  | September |  | October |  | November |  | December
Comp Plan Reference |  |  | 2017-01-18 | 2017-01-25 | 2017-02-01 | 2017-02-22 | 2017-03-01 | 2017-03-29 | 2017-04-05 | 2017-04-26 | 2017-05-03 | 2017-05-31 | 2017-06-07 | 2017-06-28 | 2017-07-05 | 2017-07-26 | 2017-08-02 | 2017-08-30 | 2017-09-06 | 2017-09-27 | 2017-10-04 | 2017-10-25 | 2017-11-01 | 2017-11-15 | 2017-12-06 | 2017-12-13
| X in Target Date for Report to TF/TTWG (SRRTTF Meeting dates: TF, TTWG, EO, Other?) |  |  | TF | TTWG,EO | TF | TTWG,EO |  | TTWG,EO | TF | TTWG,EO |  | TTWG,EO | TF | TTWG,EO? | TF | TTWG,EO? |  | TTWG, EO? | TF | TTWG, EO? | TF | TTWG, EO? | TF | TTWG, EO? | TF
| Tasks (Orange = Work Plan; Blue = no work plan, milestones in 9/14/16 Comp Plan draft | Task Assigned to?
6.3.1 Key Data Gaps | Bioaccumulation of PCBs in fish
Assessment of sediment PCB concentrations
Assessment of congener patterns
PCB sources
Bottom sediments
Fish
6.3.2 Study Plan | What is the importance of water column vs. sediment sources in contributing to fish tissue contamination?
What are the likely sources of PCBs to sediments and fish?
What are the target areas for more rigorous assessment?
Link to Comprehensive Plan Section 6.3 | Compile data
2012 Fish Data
Available Sediment data relative to fish data
Compare data
Fish tissue and water column data
Fish tissue and sediment data
[Add Link to Bud Leber Flow chart] | Conduct gap analysis

## E&O Work Plan
| Comp Plan Implementation Timeline / Tracking |  | January |  | February |  | March |  | April |  | May |  | June |  | July |  | August |  | September |  | October |  | November |  | December
Comp Plan Reference |  |  | 2017-01-18 | 2017-01-25 | 2017-02-01 | 2017-02-22 | 2017-03-01 | 2017-03-29 | 2017-04-05 | 2017-04-26 | 2017-05-03 | 2017-05-31 | 2017-06-07 | 2017-06-28 | 2017-07-05 | 2017-07-26 | 2017-08-02 | 2017-08-30 | 2017-09-06 | 2017-09-27 | 2017-10-04 | 2017-10-25 | 2017-11-01 | 2017-11-15 | 2017-12-06 | 2017-12-13
| X in Target Date for Report to TF/TTWG (SRRTTF Meeting dates: TF, TTWG, EO, Other?) |  |  | TF | TTWG,EO | TF | TTWG,EO |  | TTWG,EO | TF | TTWG,EO |  | TTWG,EO | TF | TTWG,EO? | TF | TTWG,EO? |  | TTWG, EO? | TF | TTWG, EO? | TF | TTWG, EO? | TF | TTWG, EO? | TF
| Tasks (Orange = Work Plan; Blue = no work plan, milestones in 9/14/16 Comp Plan draft | Task Assigned to?
Education and Outreach (not a specific action- but called out to develop a work plan (page 68, many action items delineate education and outreach)
Section 5.15.2, p. 68 | Develop Work Plan Changing behaviors to reduce toxics in the Spokane River Funding to enhance existing member educational efforts Educational efforts and targets Assessment of implementation Assessment of effectiveness Use of existing opportunities for education & outreach
Work Group Meets monthly (First Wednesday of month) | bar: 2017-02-01; 2017-03-01; 2017-04-05; 2017-05-03; 2017-06-07; 2017-07-05; 2017-08-02; 2017-09-06; 2017-10-04; 2017-11-01; 2017-12-06
| 1. Develop webspace for all education and outreach materials | Owners: Kristen Zimmer/Kara Whitman | bar: 2017-03-01 to 2017-04-26
| 1.1 Mock up of web space | Kristen | bar: 2017-02-01 to 2017-02-22

## Worksheet Questions
Worksheet | Cell | Question
Category B | A17 | Milestone activities will need to be reviewed and estimated times put into the schedule
Category B | X17 | Example of a date added due to Comprehensive Plan Milestone
Category B | C28 | Suggest that Urban Waters be added to this task. This would take advantage of existing Ecology/SRHD/City of Spokane partnerships
Category B | B50 | Does this schedule make sense? One year to review report? Three months to develop recommendations?
Category C | C6 | Should we start a Building Demolition and Control workgroup?
Category D | B6 | This is in the Comprehensive Plan and should be considered with respect to long term planning