## Sheet1
COMPREHENSIVE PLAN GOALS: Improve Current Efforts (Category B; Category A = no action by full SRRTTF): Dark gray = no action now; light gray = activity outside current ACE-ECY contract; no gray = suggested focus for 1/3/18
Comp Plan Goal | Goal being Addressed by SRRTTF-Funded Project? | Work Plan Needed (per Comp Plan) to Define Project? | Scope of Project that Addresses Comp Plan Goal | Lead / Workgroup | Goal(s) and/or Milestones | Next Steps, Schedule Notes
COMP PLAN ELEMENT: 5.4 Educate Local Governments about PCB-related Low Impact Development (LID) | NO. Already ongoing. | NO. | Ongoing work (not current SRRTTF project):Prepare educational materials for and make presentations to local governments concerning the benefits of LID related to PCB with an emphasis on the City of Spokane’s experience. (Third party preparation of materials)
COMP PLAN ELEMENT: 5.7 Support of Green Chemistry Alternatives | YES: Task 4 / ACE-Ecology (ECY) contract; $5K in FY'18, $5K in FY'19 | YES (Karin B. lead/drafting) | From ACE-ECY FY'18-'19 Task 4: Prepare presentation/proposal to entities, academic programs or professors. Engage with academia and other entities to pursue green chemistry alternatives. (Possible project name: Green Chemistry) | Karin B. (ECY) + workgroup: Mike P., Vikki B., Doug G. (City), Kara W., Saskia VanB (ECY), Michelle M. (EPA) | From Comp Plan Table 11, p. 67: Demonstrated tangible outreach to Ecology, EPA, &/or universities; tangible improvements in G.C. efforts due to SRRTTF actions | Develop Work Plan and Further Define Scope, milestones, timelines, effectiveness metrics.
COMP PLAN ELEMENT: 5.8 PCB Product Testing | YES: Task 3 / ACE-Ecology contract; $5K in FY'18, $5K in FY'19 | NO. Milestones, Timelines, Effectiveness Metrics in Comp Plan, Table 11 | From ACE-ECY FY'18-'19 Task 3: ID consumer products (dyes, etc.) to be tested for PCB utilizing input from previous ECY testing data & others, e.g. Solid Waste Directory. A. Determine how to best support ECY’s PCB testing efforts. This may include such activities as additional product testing for PCB content, the identification of low/no PCB containing alternatives for products previously identified, or developing strategies to distribute testing results. B. To advance PCB reductions, product testing results could be advanced to Task 4 Green Chemistry for potential development of alternatives. (Possible project name: Product Testing) | Karin B., Brandee E-M, Kari T. (Ecology) | From Comp Plan Table 11, p. 67: Comment on ECY PCB product testing report, provide input to Ecology in support of its efforts towards development of a clearinghouse, Public Ed on PCB-containing products | Review & comment on draft report when available. Draft reports with PCB testing results for different categories of products due spring 2018; goal to finalize by end of summer 2018. SRRTTF comment opportunity in spring.
COMP PLAN ELEMENT: 5.9 Waste Disposal Assistance | NO. See Ed and Outreach | YES (Mike LaScuola lead/drafting) | (Possible project name: Safe Waste) | Mike L./Vikki B. (SRHD) + workgroup: Joanie Havens, Tonilee Hansen | From Comp Plan 5.15.2, p. 67: Recommendations to implementing org's & raised public awareness on how to identify & dispose of PCB-containing items
COMP PLAN ELEMENT 5.10 Regulatory Rulemaking | Not Explicitly – overlap w/Product Testing, Green Chemistry | YES (Doug K. lead) | Comp Plan Directive: Road Paint, seek State/federal changes to color box requirements. (Possible project name: Rules & Regs) | Doug K.+ workgroup: Adriane B., Tom Agnew, Lisa D.W. | From Comp Plan 5.15.2, p. 68: Continuing dialog w/EPA & legislators re: reform of TSCA & FDA's food packaging regs; outreach to govts & paint manufacturers regarding color box requirement; & ultimately to have color box requirement changed | TSCA Workgroup or other: Discuss role of TSCA workgroup, Road paint work, PCB-11 Risk Assessment
COMP PLAN ELEMENT: 5.11 Compliance with PCB Regulations | ? | NO. Milestones, Timelines, Metrics in Comp Plan, Table 11 | From Comp Plan Table 11, p. 67: SRRTTF to provide comment on regulatory issues, review Ecology study on atmospheric transport, assess need for regulatory control of atmospheric sources based on results of study (Comp Plan Table 11, page 67) (Possible project name: Atmos.Dep) |  |  | Review & comment on draft report when available.
COMP PLAN ELEMENT: 5.12 Emerging End-of-Pipe Stormwater Technologies | SRRTTF funding for Phase 2 = TBD on 1/24/18 | NO. Milestones, Timelines, Metrics in Comp Plan, Table 11 | From Comp Plan Table 11, p. 67: SRRTTF to review Lands Council work, provide feedback, consider support of continued Phase 2 Lands Council Work (Possible project name: Fungi) | Lands Council / City of Spokane | Draft report available as of 12/4/17; review during January 2018 in advance of 1/24/18 SRRTTF meeting in preparation for decision on funding Phase 2 | Set timeline for review/comment; consider supporting Phase 2
COMP PLAN ELEMENT: 5.13 Building Demolition and Renovation Control | NO. See Ed and Outreach | YES (Cadie O. lead; workgroup meets 1/19/18) | Aspects of building demolition and renovation control are covered under Comp Plan element Education and Outreach. (Possible project name: DemoReno) | Cadie O. + workgroup: Jim Ross, Toni Taylor, Mike LaScuola, Monica Ott | From Comp Plan 5.15.2, p. 68: Adaptation of SFEP '01 report to provide guidance relevant to Spokane; coordination w/local govts to have doc distributed w/relevant permits; ultimately a demonstrated change in contractor behavior | Work plan
Education & Outreach (Comp Plan page 68) | YES: Task 5 / ACE-Ecology contract; $10K for FY'18, $15K for FY'19 | YES, (Vikki B. & Kara W. drafted straw work plan) | From ACE-ECY FY'18-'19 Task 5: In support of Comp Plan Element 5.8.2 (Conduct public education on products containing PCBs), Element 5.9.2 (Waste Disposal Assistance), Element 5.13 (Building Demolition and Renovation Control), & Element 5.15.2 (Actions that Require Development of New Work Plans), the following outreach materials will be completed to increase business and public awareness (including, but not limited to): a. A website for the SRRTTF b. How to identify and dispose of PCB-containing items c. How to adjust purchasing practices to select products with lower PCB content d. An info package & checklist for use by agencies that make site visits to businesses on PCB issues & management e. Public ed & outreach materials on PCB waste disposal and selecting products with lower PCB content f. Adapting San Fran Estuary Project (SFEP) document to make it suitable for use as a guidance document for Spokane-area building contractors on how to reduce PCB load during demolition & remodeling g. Benefits of Low Impact Development (Possible project names E&O1, E&O2, etc.) | Vikki Barthels + E&O Workgroup: Kara W., Kristen Zimmer, Toni Taylor, Jerry W., Karin B. | from ACE-ECY contract: 1/31/18: functional website URL; 6/30/19: copies of outreach materials prepared. from Comp Plan: The E&O workgroup will "explore additional funding to enhance existing member educational efforts. The group will implement a comprehensive outreach strategy w/measurable targets to assess implementation & outreach effectiveness...the SRRTTF will also optimize existing opportunities (events/media) to change behaviors & reduce PCB loading to the Spokane River."
COMPREHENSIVE PLAN GOALS: New Control Actions (Category C):
Comp Plan Goal | Goal being Addressed by SRRTTF-Funded Project? | Work Plan Needed (per Comp Plan) to Define Project? | Funded Project that Addresses Comp Plan Goal | Lead | Potential Milestones | Next Steps, Schedule Notes
COMP PLAN ELEMENT: 5.14 Identification of Sites of Concern for Contaminated Groundwater | YES: Task 1 / ACE-Ecology contract; $45K in FY'18, $25K in FY'19 | YES (Bud Leber lead) | Study Groundwater (GW) Upgradient of Kaiser at Industrial Park (Possible project name: Kaiser Upgradient) From ACE-ECY FY'18-'19 Task 1: Develop Plan for Identification of Suspected PCB Sources Up-gradient of Kaiser Aluminum A. Mine existing data to assess potential significance of GW sites contributing PCBs to River. B. Compile and review all up-gradient GW & related data collected by Kaiser Aluminum C. Work w/TCP to develop a strategy & sampling plan (QAPP) to determine location of suspected PCB sources in vicinity of Spokane Industrial Park. D. If needed, this could include placement & sampling of new GW monitoring wells | Bud Leber + Workgroup: Mike Hermanson, Jim Ross, Sandy T. & Jeremy S. (Ecology) | from Comp Plan: Assessment doc describing data mining activities; coordination w/TCP resulting in consensus plan for future action; determine whether each site under consideration is contributing sufficient PCBs to River to merit remediation; initiation of remediation on sites determined to be significant. PLUS (Task1): 1/30/18: A report of all existing GW data and related information from the industrial park area; 4/1/18: The strategy and sampling plan for determining the location of suspected PCB sources; 6/30/19: Final report of the results of the work including documenting any installation of groundwater monitoring wells and groundwater sampling results; (Task2): Quarterly progress reports; 6/30/18: QAPP; 3/30/19: Progress report describing all sampling related activities & an assessment of GW loading to River in Upriver Dam to Greene Street reach; 6/30/19: A draft report of the correlation validation efforts with respect to PCB homologue patterns between calculated river loading from groundwater in the gaining reach and the contaminated groundwater site. (Task6): Quarterly progress reports; 3/31/18: Scope of work; 6/30/18: Contract with Dr. Rodenburg; 6/30/19: Final report (if data available) | Workgroup to finalize scope of work, milestones, deliverables and schedule and subcontract to conduct the work. Initiate work with subcontractor.
COMP PLAN ELEMENT: 5.14 Identification of Sites of Concern for Contaminated Groundwater | YES: Task 2 / ACE-Ecology contract; $20K in FY'18, $60K in FY'19 | YES (Bud Leber lead) | PCB Mass Balance (Plantes Ferry Pk/Upriver Dam/Greene St) (Possible project name: Mass balance Plantes-Greene) From ACE-ECY FY'18-'19 Task 2: Collect dry weather flow data & ambient surface water samples from Plantes Ferry Park to Nine Mile reaches to better determine impacts of gaining & losing reaches in this area. Upriver Dam sampling location will provide data for assessing impacts of GW entering gaining reach between Upriver Dam & Greene Street where a known PCB contaminated GW site is. This data will be used to validate the previous correlation efforts with respect to PCB homologue patterns between the calculated river loading from GW in gaining reach and the contaminated GW site. / Coordinate with synoptic sampling to address Barker Road to Plantes Ferry Park GW contribution & track concentration changes. / GW sampling may be conducted at former GE site to determine GW flow direction & support PCB homolog pattern analysis. | Bud Leber, Dave Dilks, Jim Ross |  | Workgroup to finalize scope, milestones, deliverables and schedule and subcontract to conduct the work. Initiate work with subcontractor. Aug-Sept (Low Flows); best if simultaneous w/Mass Balance Assessment from Spokane gage to Nine Mile
COMP PLAN ELEMENT: 5.14 Identification of Sites of Concern for Contaminated Groundwater | YES: Task 6 / ACE-Ecology contract; $20K in FY'18, $20K in FY'19 | YES (Bud Leber lead) | Watershed-Wide PMF Analysis (Possible project name: PMF) From ACE-ECY FY'18-'19 Task 6: A. Develop a scope of work for the analysis given available data & identify what additional data, if any, needs to be collected. B. (ACE) Develop a sub-contract with Dr. Rodenburg at Rutgers to perform PMF or related analysis. C. If data is available, complete PMF or related analysis. If analysis can be completed, complete a final report documenting findings of PMF analysis by 6/30/19 | Rob Lindsay (Spokane County) |  | Workgroup to finalize scope, milestones, deliverables & schedule, & subcontract to conduct work. Initiate work w/subcontractor. Schedule dependent on formatting data. ID who will process data if database work not completed.
COMP PLAN ELEMENT: 5.14 Identification of Sites of Concern for Contaminated Groundwater | YES ~$50K (not via ACE-ECY contract; potential for EAP assistance) | YES (Bud Leber lead) | PCB Mass Balance (Spokane gage to Nine Mile gage) (Possible project name: Mass balance Spokane-Nine Mile) Collect dry weather flow data and surface water samples from these three locations to better determine the impact of the gaining reaches in the area. Groundwater flow into these reaches of the river has not yet been evaluated for PCB contribution. (This work could also provide monitoring data based upon the option selected.) | Bud Leber, Dave Dilks, Jim Ross |  | Workgroup to finalize scope, milestones, deliverables and schedule and subcontract to conduct the work. Initiate work with subcontractor. Aug-Sept (Low Flows); best if simultaneous w/Mass Balance Assessment from Plantes Ferry Park to Greene St.
COMPREHENSIVE PLAN GOALS: Future Activities (Comp Plan Element 6)
COMP PLAN ELEMENT: 6.1 Implementation Effectiveness Assessment | NO | NO | No funded project; annual Implementation Review Summary and five-year Implementation Assessment Report | SRRTTF | Implementation Review Summary to be completed by one year after issuance of Comp Plan (January 2018)
COMP PLAN ELEMENT: 6.2 Consideration of Additional Control Actions (from Comp Plan p. 70: "The commitment to these actions is to give them future consideration, but with no specific commitment towards implementation at this time."): 6.2.1 Education on Septic Disposal; 6.2.2 Survey Schools & Public Buildings; 6.2.3 Accelerated Sewer Construction; 6.2.4 Emerging Wastewater Technology; 6.2.5 Survey Local Electrical Equipment; 6.2.6 Leak Prevention/ Detection in Electrical Equipment; 6.2.7 Regulation of Waste Disposal; 6.2.8 Stormwater Source Tracing; 6.2.9 Removal of Carp from Lake Spokane; 6.2.10 PCB Identification During Inspection; 6.2.11 Compliance with PCB Regulations
COMP PLAN ELEMENT: 6.3 Studies to Address Data Gaps: 1. Bioaccumulation of PCBs in Fish (workgroup lead=Chris D. (WDFW), group = Dave Dilks, Karin B/Brandee E-M, Ben Brattebo (Spokane C.), Cadie Olsen, Doug K., Monica Ott, Bud L, Lisa D.W.); Second Data Gap Study: Assessment of Sediment PCB Concentrations
Non-Comp Plan: Facilitation contract w/Ruckelshaus Center through 6/30/18 (~$80K); Technical support contract w/LimnoTech through 12/31/18 (~$65K)