## WorkByCompPlanElement
COMPREHENSIVE PLAN GOALS: Improve Current Efforts (Category B; Category A = no action by full SRRTTF): Dark gray = no action now; light gray = activity outside current ACE-ECY contract; no gray = suggested focus for 1/3/18
Project Identifier* | Comp Plan Element | SRRTTF Resources in Support of Work | Work Plan Needed (per Comp Plan) to Define? | Scope of Project that Addresses Comp Plan Goal | Lead / Workgroup | Goal(s) and/or Milestones | Next Steps, Schedule Notes
5.7-GC2017AE4 | 5.7 Support of Green Chemistry Alternatives | ACE-ECY contract (Task 4): $5K in FY'18, $5K in FY'19 | YES (Karin B. lead/drafting) | From ACE-ECY FY'18-'19 Task 4: Prepare presentation/proposal to entities, academic programs or professors. Engage with academia and other entities to pursue green chemistry alternatives. | Karin B. (ECY) + workgroup: Mike P., Vikki B., Doug G. (City), Kara W., Saskia VanB (ECY), Michelle M. (EPA) | From Comp Plan Table 11, p. 67: Demonstrated tangible outreach to Ecology, EPA, &/or universities; tangible improvements in G.C. efforts due to SRRTTF actions | Develop Work Plan and Further Define Scope, milestones, timelines, effectiveness metrics. Target Date?
5.8-PT2017AE3 | 5.8 PCB Product Testing | ACE-ECY contract (Task 3): $5K in FY'18, $5K in FY'19 | NO. Milestones, Timelines, Effectiveness Metrics in Comp Plan, Table 11 | From ACE-ECY FY'18-'19 Task 3: ID consumer products (dyes, etc.) to be tested for PCB utilizing input from previous ECY testing data & others, e.g. Solid Waste Directory. A. Determine how to best support ECY’s PCB testing efforts. This may include such activities as additional product testing for PCB content, the identification of low/no PCB containing alternatives for products previously identified, or developing strategies to distribute testing results. B. To advance PCB reductions, product testing results could be advanced to Task 4 Green Chemistry for potential development of alternatives. | Karin B., Brandee E-M, Kari T. (Ecology). Note: coordinate scope with element 5.10 | From Comp Plan Table 11, p. 67: Comment on ECY PCB product testing report, provide input to Ecology in support of its efforts towards development of a clearinghouse, Public Ed on PCB-containing products | Review & comment on draft report(s) when available (draft reports w/testing results for different categories of products due spring 2018; goal to finalize by end of summer 2018. SRRTTF comment opportunity in spring.
5.9-WDA-WG-SRHD+E&O | 5.9 Waste Disposal Assistance | Staff Time from SRHD, E&O workgroup, dischargers' PIOs | YES (Mike LaScuola lead/drafting) | From Comp Plan 5.15.2, p. 67: Recommendations to implementing org's & raised public awareness on how to identify & dispose of PCB-containing items. SRHD doing ongoing work with Waste Directory (c/o EnviroStars Steering Committee) related to proper disposal of waste potentially containing PCBs. Test effacacy of website information--see also Ed and Outreach #b and e. | Mike L./Vikki B. (SRHD) + workgroup: Joanie Havens, Tonilee Hansen | From TTWG 1/3/18: DRAFT goals for 2018: establish mechanism to track # of web hits regarding Waste Directory; develop plan to measure behavior change (c/o Robinson Research baseline survey) | Draft work plan (goal by 1/17/18)
5.10-RR-WG-IEP+DOT+ECY+DES | 5.10 Regulatory Rulemaking | Staff time from workgroup (+ some overlap w/Product Testing, Green Chemistry) | YES (Doug K. lead) | Comp Plan: Seek changes to state/federal Road Paint color box requirements. Workgroup lead (1/3/18 TTWG) reports 5 issues: 1) Road paint (low-PCB product meets WSDOT needs--contact DES so they know & purchase; 2) Consider a pilot project to address use of low-PCB Printing inks; 3) EPA TSCA allowance (no movement currently); 4) PCB-11 risk assessment (work w/EPA to get it started); 5) Food packaging (work w/FDA to encourage low-PCB alternatives) | Doug K.+ workgroup: Adriane B., Tom Agnew, Lisa D.W.. Note: coordinate with element 5.8 efforts | From Comp Plan 5.15.2, p. 68: Dialog w/EPA & legislators re: reform of TSCA & FDA's food packaging regs; outreach to govts & paint manufacturers re: color box requirement & ultimately get it changed. From TTWG 1/3/18: 2018 DRAFT Goal (?): gauge poential for low-PCB inks | Draft work plan (goal by 1/17/18)
5.11-CwRegs-TF-EAP/ECY | 5.11 Compliance with PCB Regulations | Staff time from SRRTTF member entities | NO. Milestones, Timelines, Metrics in Comp Plan, Table 11 | SRRTTF comment on regulatory issues, review Ecology study on atmospheric transport & assess need for regulatory control of atmospheric sources based on results of study. |  | From Comp Plan Table 11, p. 67: SRRTTF to provide comment on regulatory issues, review Ecology study on atmospheric transport, assess need for regulatory control of atmospheric sources based on results of study. | Review & comment on draft report when available.
5.12-SWTech-LC | 5.12 Emerging End-of-Pipe Stormwater Technologies | Staff time (Land Council, City of Spokane); maybe SRRTTF $15K (for Phase 2) | NO. Milestones, Timelines, Metrics in Comp Plan, Table 11 | From Comp Plan Table 11, p. 67: SRRTTF to review Lands Council work, provide feedback, consider support of continued Phase 2 Lands Council Work | Lands Council / City of Spokane | Draft report available as of 12/4/17; review during January 2018 in advance of 1/24/18 SRRTTF meeting in preparation for decision on funding Phase 2 | Set timeline for review/comment; consider supporting Phase 2
5.12.2-E&O2017AE-WG | 5.12.2 sub-element Education & Outreach (also involved in 5.8.2, 5.9.2, 5.13, 5.15.2) | ACE-ECY contract (Task 5): $10K for FY'18, $15K for FY'19 (From TTWG 1/3/18: Also possibility for Riverkeeper public participation grant to supply staff time or other resources) | YES, (Vikki B. & Kara W. drafted straw work plan) | From ACE-ECY FY'18-'19 Task 5: In support of Comp Plan Element 5.8.2 (Conduct public education on products containing PCBs), Element 5.9.2 (Waste Disposal Assistance), Element 5.13 (Building Demolition and Renovation Control), & Element 5.15.2 (Actions that Require Development of New Work Plans), the following outreach materials will be completed to increase business and public awareness (including, but not limited to): a. A website for the SRRTTF b. How to identify and dispose of PCB-containing items c. How to adjust purchasing practices to select products with lower PCB content d. An info package & checklist for agency use in site visits to businesses on PCB issues & management e. Public ed & outreach materials on PCB waste disposal and selecting products with lower PCB content f. Adapting San Fran Estuary Project (SFEP) document to make it suitable for use as a guidance document for Spokane-area building contractors on how to reduce PCB load during demolition & remodeling g. Benefits of Low Impact Development | Vikki Barthels + E&O Workgroup: Kara W., Kristen Zimmer, Toni Taylor, Jerry W., Karin B. | from ACE-ECY contract: 1/31/18: functional website URL; 6/30/19: copies of outreach materials prepared. from Comp Plan: The E&O workgroup will "explore additional funding to enhance existing member educational efforts. The group will implement a comprehensive outreach strategy w/measurable targets to assess implementation & outreach effectiveness...the SRRTTF will also optimize existing opportunities (events/media) to change behaviors & reduce PCB loading to the Spokane River." | Meeting 1/10/18 to identify goals for 2018, refine website; present website to SRRTTF 1/24/18. Draft scope of work by 1/17/18.
5.13-DemoControl-WG+E&O | 5.13 Building Demolition and Renovation Control | Staff time from SRRTTF entities; possbility for E&O funds to assist | YES (Cadie O. lead; workgroup meets 1/19/18) | Aspects of building demolition and renovation control are covered under Comp Plan element Education and Outreach. | Cadie O. + workgroup: Jim Ross, Toni Taylor, Mike LaScuola, Monica Ott | From Comp Plan 5.15.2, p. 68: Adaptation of SFEP '01 report to provide guidance relevant to Spokane; coordination w/local govts to have doc distributed w/relevant permits; ultimately a demonstrated change in contractor behavior | Work plan (following 1/19/18 workgroup meeting); anticipated direct coordination with E&O workgroup to disseminate info
COMPREHENSIVE PLAN GOALS: New Control Actions (Category C):
Project Identifier | Comp Plan Element | SRRTTF Resources in Support of Work | Work Plan Needed (per Comp Plan) to Define? | Scope of Project that Addresses Comp Plan Goal | Lead | Potential Milestones | Next Steps, Schedule Notes
5.14-GWUK2017AE1 | 5.14 Identification of Sites of Concern for Contaminated Groundwater | ACE-ECY contract (Task 1): $45K in FY'18, $25K in FY'19 | YES (Bud Leber lead) | Study Groundwater (GW) Upgradient of Kaiser at Industrial Park From ACE-ECY FY'18-'19 Task 1: Develop Plan for Identification of Suspected PCB Sources Up-gradient of Kaiser Aluminum A. Mine existing data to assess potential significance of GW sites contributing PCBs to River. B. Compile and review all up-gradient GW & related data collected by Kaiser Aluminum C. Work w/TCP to develop a strategy & sampling plan (QAPP) to determine location of suspected PCB sources in vicinity of Spokane Industrial Park. D. If needed, this could include placement & sampling of new GW monitoring wells | Bud Leber + Workgroup: Mike Hermanson, Jim Ross, Sandy T. & Jeremy S. (Ecology) | from Comp Plan: Assessment doc describing data mining activities; coordination w/TCP resulting in consensus plan for future action; determine whether each site under consideration is contributing sufficient PCBs to River to merit remediation; initiation of remediation on sites determined to be significant. PLUS (Task1): 1/30/18: A report of all existing GW data and related information from the industrial park area; 4/1/18: The strategy and sampling plan for determining the location of suspected PCB sources; 6/30/19: Final report of the results of the work including documenting any installation of groundwater monitoring wells and groundwater sampling results; (Task2): Quarterly progress reports; 6/30/18: QAPP; 3/30/19: Progress report describing all sampling related activities & an assessment of GW loading to River in Upriver Dam to Greene Street reach; 6/30/19: A draft report of the correlation validation efforts with respect to PCB homologue patterns between calculated river loading from groundwater in the gaining reach and the contaminated groundwater site. (Task6): Quarterly progress reports; 3/31/18: Scope of work; 6/30/18: Contract with Dr. Rodenburg; 6/30/19: Final report (if data available) | Draft scope for SRRTTF 1/24/18 (to be finalized by workgroup with ACE & contractors including milestones, deliverables and schedule); subcontract to conduct the work; initiate work with subcontractor.
5.14-GWUK-MB2017AE2 | 5.14 Identification of Sites of Concern for Contaminated Groundwater | ACE-ECY contract (Task 2): $20K in FY'18, $60K in FY'19. NOTE: project will require additional funds (this estimate only for Plantes Ferry to Greene St.) | Yes for 5.14 overall; not required by Comp Plan for this particular project | PCB Mass Balance: PCB Mass Balance (Plantes Ferry Pk/Upriver Dam/Greene St + Spokane gage to Nine Mile gage) From ACE-ECY FY'18-'19 Task 2: Collect dry weather flow data & ambient surface water samples from Plantes Ferry Park to Nine Mile reaches to better determine impacts of gaining & losing reaches in this area. Upriver Dam sampling location will provide data for assessing impacts of GW entering gaining reach between Upriver Dam & Greene Street where a known PCB contaminated GW site is. This data will be used to validate the previous correlation efforts with respect to PCB homologue patterns between the calculated river loading from GW in gaining reach and the contaminated GW site. / Coordinate with synoptic sampling to address Barker Road to Plantes Ferry Park GW contribution & track concentration changes. / GW sampling may be conducted at former GE site to determine GW flow direction & support PCB homolog pattern analysis.Collect dry weather flow data and surface water samples from these three locations to better determine the impact of the gaining reaches in the area. | Bud Leber, Dave Dilks, Jim Ross |  | QAPP development--Sampling to occur Aug-Sept (Low Flows). Draft scope for SRRTTF 1/24/18 (to be finalized by workgroup with ACE & contractors including milestones, deliverables and schedule); subcontract to conduct the work; initiate work with subcontractor.
5.14-GWUK2017AE6 | 5.14 Identification of Sites of Concern for Contaminated Groundwater | ACE-ECY contract (Task 6): $20K in FY'18, $20K in FY'19 NOTE: project will require additional funds | Yes for 5.14 overall; not required by Comp Plan for this particular project | Watershed-Wide PMF Analysis From ACE-ECY FY'18-'19 Task 6: A. Develop a scope of work for the analysis given available data & identify what additional data, if any, needs to be collected. B. (ACE) Develop a sub-contract with Dr. Rodenburg at Rutgers to perform PMF or related analysis. C. If data are available, complete PMF or related analysis. If analysis can be completed, complete a final report documenting findings of PMF analysis by 6/30/19 | Rob Lindsay (Spokane County) |  | Draft scope for 1/24/18 (workgroup finalize w/ACE & contractors including milestones, deliverables & schedule); subcontract by June 2018, consider analysis after 2018 mass balance results are available. Schedule depends on data formatting. ID who will process data if database not completed.
COMPREHENSIVE PLAN GOALS: Future Activities (Comp Plan Element 6)
6.1-IRS | 6.1 Implementation Effectiveness Assessment | NO | NO | No funded project; annual Implementation Review Summary and five-year Implementation Assessment Report | SRRTTF | Implementation Review Summary to be completed by one year after issuance of Comp Plan (January 2018) | Task Force consider approving Implementation Review Summary on 1/24/18
N/A | 6.2 Consideration of Additional Control Actions (Comp Plan p. 70: "The commitment to these actions is to give them future consideration, but with no specific commitment towards implementation at this time."): 6.2.1 Education on Septic Disposal; 6.2.2 Survey Schools & Public Buildings; 6.2.3 Accelerated Sewer Construction; 6.2.4 Emerging Wastewater Technology; 6.2.5 Survey Local Electrical Equipment; 6.2.6 Leak Prevention/ Detection in Electrical Equipment; 6.2.7 Regulation of Waste Disposal; 6.2.8 Stormwater Source Tracing; 6.2.9 Removal of Carp from Lake Spokane; 6.2.10 PCB Identification During Inspection; 6.2.11 Compliance with PCB Regulations TTWG 1/3/18 chose not to suggest any activities on these for 2018
N/A | 6.3-Studies to Address Data Gaps: 1. Bioaccumulation of PCBs in Fish (workgroup lead=Chris D. (WDFW), group = Dave Dilks, Karin B/Brandee E-M, Ben Brattebo (Spokane C.), Cadie Olsen, Doug K., Monica Ott, Bud L, Lisa D.W.); Second Data Gap Study: Assessment of Sediment PCB Concentrations Fish Sampling workgroup met 1/9/18 to discuss both
Needed? | Non-Comp Plan: Facilitation contract w/Ruckelshaus Center through 6/30/18 (~$85K); Technical support contract w/LimnoTech through 12/31/18 (~$65K)

## ACE-ECY project tracking
ACE Contract # C1800094 Project Planner
| Select a period to highlight at right. A legend describing the charting follows. | [6 empty] | Period Highlight: | 7 |  |  | Plan Duration | [5 empty] | Actual Start |  |  |  |  | % Complete |  |  |  |  | Actual (beyond plan)
| ACTIVITY | PLAN START | PLAN DURATION | ACTUAL START | ACTUAL DURATION | TOTAL | % BUDGET | PERCENT COMPLETE | PERIODS
[6 empty] | BUDGET | SPENT |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24
Task 1: Identification of sources upgradient of Kaiser | Task 1 - progress report of activities & associated costs | 1 | 24 | 4 | 21 |  |  | 0%
| Task 1 - memo comparing homolog patterns | 1 | 24 | 4 | 1 |  |  | 100%
| Task 1 - report of data and information from industrial park area | 1 | 24 | 7 | 1 |  |  | 0%
| Task1 - strategy & sampling plan | 1 | 24 | 9 | 1 |  |  | 0%
| Task 1 - final report | 1 | 24 | 23 | 2 |  |  | 0%
Task 2: Perform mass balance from Plantes Ferry to Nine Mile | Task 2 - progress report of activities & associated costs | 1 | 24 | 4 | 21 |  |  | 0%
| Task 2 - QAPP | 1 | 24 | 12 | 1 |  |  | 0%
| Task 2- progress report of sampling activities and assessment of GW loading | 1 | 24 | 9 | 1 |  |  | 0%
| Task 2 - draft report | 1 | 24 | 24 | 1 |  |  | 0%
Task 3: Product Testing | Task 3 - progress report of activities & associated costs | 1 | 24 | 4 | 21 |  |  | 0%
| Task 3 - report documenting data, results, and/or strategy | 1 | 24 | 23 | 2 |  |  | 0%
Task 4: Green chemistry advancement | Task 4 - progress report of activities & associated costs | 1 | 24 | 4 | 21 |  |  | 0%
| Task 4 - matrials and presentation prepared | 1 | 24 | 12 | 1 |  |  | 0%
Task 5: Develop Outreach Materials | Task 5 - progress report of activities & associated costs | 1 | 24 | 4 | 21 |  |  | 0%
| Task 5 - functional website URL | 1 | 24 | 1 | 7 |  |  | 75%
| Task 5 - copies of outreach material prepared | 1 | 24 | 4 | 21 |  |  | 20%
Task 6: Conduct watershed-wide PMF Analysis | Task 6 - progress report of activities & associated costs | 1 | 24 | 4 | 21 |  |  | 0%
| Task 6 - scope of work | 1 | 24 | 9 | 1 |  |  | 10%
| Task 6 - contract with Dr. Rodenburg | 1 | 24 | 12 | 1 |  |  | 0%
| Task 6 - final report | 1 | 24 | 23 | 2 |  |  | 0%
Task 7: Limnotech technical support | Task 7 - progress report or list of requests or activities & associated costs | 1 | 24 | 4 | 21 |  |  | 0%
Task 8: ACE administration | Task 8 - progress report of activities & associated costs | 1 | 24 | 4 | 21 |  |  | 0%
| Task 8 - EIM data entry verification | 1 | 24 | 24 | 1 |  |  | 0%